# ARPG

# The Agile Release Planning Game

# Extended Version: The lost art of communication

Facilitator’s guide – version 1.2 July 2010

A game where participants run an agile project. Invented by James King (www.kingsinsight.com) and extended by Eduardo Meira Peres (eduardo.peres@pucrs.br).

Contents

The game	3

The story so far	3

What needs to be done	3

The strategy	3

Getting started	4

Break the group into teams	4

Explain the story so far	4

Set up the board	4

Explain the sprint goals	4

Explain velocity and story points	4

Prepare an initial release plan	4

Running the first iteration	4

Confirm the plan for the iteration	4

Determine the actual velocity	5

Impacts of the actual velocity	5

Identify new defects	5

Identify new technical debt	5

Update the status reporting sheet	5

Running remaining iterations	6

Embrace Change	6

Ending the game	6

Debrief	6

Copyright	6

# The game

The game is designed to help participants understand the concepts involved in release and iteration planning.

Participants must plan their work across a series of iterations, which we will call sprints, and then adapt their plans as the project evolves.

In order to be successful, participants must meet critical deadlines, minimise defects, monitor their velocity and replan as they gain further insight into the evolving project.

## The story so far

“NE 1 L8 – CU L8R”. The process of language simplification that was accelerated by the advent of the internet has reached its climax. In this scenario, the people of a certain city have completely forgotten the meaning of the letters, and therefore can’t communicate through written or spoken language.

## What needs to be done

In order to recover the ability to communicate in this community each participant was designated a team whose mission was to rebuild the maximum number of letters of the alphabet as possible. This will allow the gradual return of the lost art of communication.

At the end, the mission should reach the following criteria:

- It should be possible to construct the phrase: “It’s difficult to put it into words”. Notice that this phrase doesn’t contain the vowels A and E. This is important for the game.

- The product must have less than 6 unresolved defects.

## The strategy

Due to the urgent need to communicate for the survival of the residents, the chosen strategy was a rapid and graduated construction of the letters that will be delivered to the population in 4 (four) cycles of short duration called sprints.

The mission computer produced a series of story cards for the team to use. There are two types of cards. The first type are cards containing the name of a letter or a special punctuation mark, and the number of “story points” required to build this character. These cards are used by  the team to produce the deliverables.

The second type of cards have a special meaning: Tech Debt (to reduce the technical debt of project) and Bugs (to fix defects), and a blank space that must be filled in by the team with the exact number of Tech Debt or Bugs that will be addressed at the sprint.

The amount of story points the team can complete each sprint (or iteration) is known as the team’s velocity.

The computer estimates that the team’s velocity is approximately 25 story points per sprint. This number is expected to change over time as the mission evolves.

The computer has also produced some other tools for the team to use:

- A status report for the team to use in tracking their progress and

- A game board for the team to use in planning sprints and registering the results

# Getting started

The game can be introduced by first presenting an explanation of the concepts of release planning or it can be run prior to the explanation of the theory.

## Break the group into teams

To introduce the game, break the group into teams. Each team will need:

- Team members. The best team size is between 2 and 8 people.

- The game board.

- The set of story cards.

- A pair of die.

- A status report sheet and a pen.

## Explain the story so far

Explain the background story to the group.

## Set up the board

Have each team lay the board out in front of them.

## Explain the sprint goals

At each sprint the team should complete stories to meet the sprint goal.

Each sprint must have the following goals:

| Sprint | Goal |
| --- | --- |
| Sprint 1 | Construction of a minimum of two words with two or more letters. |
| Sprint 2 | Construction of a minimum of two words with four or more letters. |
| Sprint 3 | Construction of two complete grammaticaly correct sentences. |
| Sprint 4 | Construction of the sentence which is the object of this mission |

Obs: 1) You are not permitted to use a Word more than once in the game; 2) You can freely repeat the letters you have constructed.

## Explain velocity and story points

Each story is represented by a story card. Each card has a heading, a story name and a story point rating or  blank spaces that must be filled in by the team

- The story point rating is the cost to complete the story.

- The velocity is the number of story points the team can expend to complete stories each sprint.

## Prepare an initial release plan

The final step in the initiation phase of the project is to prepare a release plan.

Give each team 10 minutes to:

- Review the project rules and objectives; and

- Come up with a release plan.

Note, at the end of the game the team will have executed 4 sprints, but initially they must allocate stories at least to the first sprint.

# Running the first iteration

## Confirm the plan for the iteration

The team confirms the stories to be attempted before the start of the sprint.

In the subsequent iterations, the team needs to decide whether to reduce outstanding defects and technical debts. Fixing a defect requires 1 story point per defect. Each technical debt also requires 1 story point per technical debt.

However, in the first iteration there will be neither  defects to fix nor technical debts to solve. So the team should place the “zero” defects and   technical debt at start  on the status report.

## Determine the actual velocity

We predict that the velocity for the first iteration will be 25. This is a good indicator of how much work the team will get done, but it is not a perfect prediction.

So we roll dice to represent the impact of unpredicted occurrences, as well as the ongoing improvements made by the team.

Have each team roll two dice to evaluate the actual  velocity as below.

The first die represents the gains of improving the team performance and the result must be added to the planned velocity.

The second die represents distractions and impediments that reduce the performance and must then be subtracted from the planned velocity.

So, complete the status report with the following formula:

Actual velocity = Expected Velocity + die (first) – die (second)

## Impacts of the actual velocity

If the actual velocity is greater than planned, the team can insert new items into the sprint (new stories, correction of defects or reduction of the technical debt) until the total is complete.

But, if the actual velocity is unfortunately less than planned, the team should remove as many items as necessary.  The items to be removed are those of less priority and should be postponed until the following sprint.

This actual velocity will also be the expected velocity for the next sprint.

Complete the status report with the following formula for the next sprint:

Expected velocity (sprint x+1) = actual velocity(sprint x)

## Identify new defects

After that, update the project metrics as follows:

- Update the remaining defects subtracting them from the actual defects fixed in the sprint.

- If there are still remaining defects, the number of defects must be multiplied by 2 (as the time passes, the cost of fixing defects is higher).

- Roll the die and find how many new defects were injected but not fixed during the sprint. Update the remaining defects adding this number.

## Identify new technical debt

- Update the remaining technical debt subtracting it from the actual technical debt solved.

- Roll the die and quantify the new technical debt created during the sprint. Update the remaining technical debt adding this number. Advise the team of the following condition: If the remaining technical debt reaches 10 the project will be canceled.

## Update the status reporting sheet

The team update the status report to reflect what has occurred during the iteration.

# Running remaining iterations

If the team has reached the goal of the sprint they now move onto the next sprint.

The process is essentially the same as running the first sprint, except that defects and technical debt may now exist.

# Embrace Change

At the  end of sprint 2 or 3 communicate to the team that the goal of the project needs to be changed to construct the phrase  “It’s really difficult to put it into words” (adding the letters E and A to the scope).

Thus the team will experience how changes are incorporated into the project

# Ending the game

For a single team, the game ends after the 4th sprint.

If more than one team is playing then other teams can continue, or the game can end for the whole group if preferred.

# Debrief

Once the teams have completed the game, perform a debrief as a group.

One way to do this is to hold a retrospective:

- Have each team answer 3 questions:

  - What worked well?

  - What caused problems?

  - What can we learn from this?

- If there are multiple teams, then have the teams discuss their findings as a group.

# Copyright

This work (The Agile Release Planning Game and the materials associated with it) is licensed under the Creative Commons Attribution 3.0 Unported License.

You may reproduce and use the game subject to the terms of that license, subject to attributing the game’s creation to James King and by including my website or contact details on the game board.

To view a copy of this license, visit http://creativecommons.org/licenses/by/3.0/ or send a letter to Creative Commons, 171 Second Street, Suite 300, San Francisco, California, 94105, USA.

It would also be appreciated if you could send feedback to Eduardo.peres@pucrs.br if you enjoy the game.